## Sheet1
Danielle Thoreson's Timeline for Python FS Project
| Thursday- W3D4 | Friday- W3D5 | Saturday- W3D6 | Sunday- W4D1 | Monday- W4D2 | Tuesday- W4D3 | Wednesday- W4D4 | Thursday- W4D5 | Friday- W4D6
Planning | Planning and Prep
Prototype |  | Clickable Prototype
Features |  |  |  |  | DB and CRUD Functionality
API Integration- Goodreads
APOI Integration- Spotify
Deployment | [6 empty] | Add to GIT and Push
Presentation | [8 empty] | Present